## Sheet1
DataXAi Development Tracker
Note: Research/thesis evidence and software implementation evidence are separate. A passing pytest run does not prove a research hypothesis or thesis result.
Volume | Scope | Status | Evidence / Check | Owner | Notes / Risks | Next Action | Ready For Next Volume?
Volume 1 | Foundations | LOCALLY VERIFIED | Foundation and architecture are documented in the handbook; historical milestone evidence.
Volume 2 | Environment & Repository | LOCALLY VERIFIED | Environment/Docker setup is in place. Application database migration recovery is recorded under Volume 3 (2026-10-11).
Volume 3 | Database, Auth & Core | LOCALLY VERIFIED | 2026-10-11 app DB recovery: db healthy on localhost:5432; database/role dataxai/dataxai. public tables: 0 before migration; read-only plan listed initial Django migrations; migrate completed with all planned entries OK; showmigrations showed all [X]; manage.py check clean; final public table count: 22. Effective Django DB settings: dataxai/dataxai at localhost:5432. |  | Local application database bootstrap and migration state verified. This does not verify end-to-end application behavior or production readiness.
Volume 4.1 | ETL Prerequisites | LOCALLY VERIFIED | Historical dataset/prerequisite work is recorded; full UCI processing was not rerun today.
Volume 4.2 | ETL Source Abstraction | LOCALLY VERIFIED | CSV, Excel, and real source-PostgreSQL tests pass in today’s full suite.
Volume 4.3.1 | Transform contract and alias mapping | IMPLEMENTED / LOCALLY VERIFIED; OWNER ACCEPTANCE PENDING | Commit 136c6db. Full suite: 89 passed, 0 skipped. Focused PostgreSQL/source/transform suite: 28 passed. Ruff, Black, isort, Django system check, and Compose config passed. |  | Historical app DB authentication/migration-history caveat was superseded by the Volume 3 local recovery on 2026-10-11; database recovery is separate from ETL 4.3.1. | Project-owner review and acceptance of 4.3.1. | No
Volume 4.3.1a | Duplicate canonical-column protection | PLANNED - NOT STARTED | Duplicate canonical-column protection and dedicated tests; gated on 4.3.1 review and owner acceptance. |  |  | After 4.3.1 acceptance, implement and verify the duplicate-column protection. | No
Volume 4.3.2 | Type coercion | PLANNED - NOT STARTED | Type coercion is not started; blocked until 4.3.1 and 4.3.1a are integrated, locally verified, reviewed, and accepted. |  |  | Wait for 4.3.1 and 4.3.1a integration, local verification, review, and owner acceptance. | No
Remaining Volume 4.3 | dates/business rules | PLANNED | Specify date/timezone and unresolved data-case policies before implementing them.
Volume 4.4 | ETL Load Layer | PLANNED | Not implemented.
Volume 4.5 | PipelineRun Integration | PLANNED | Not implemented.
Volume 4.6 | ETL Error Handling | PLANNED | Not implemented as the later pipeline-level milestone.
Volume 4.7-4.8 | ETL Testing | PLANNED | Tests exist for earlier ETL slices; later hardening remains.
Volume 4.9 | ETL Verification Checkpoint | PLANNED | End-to-end pipeline checkpoint remains ahead.
Volume 5 | Data Validation Engine | PLANNED | Validation app exists; full engine remains ahead.
Volume 6 | Auto-Healing Engine | PLANNED | Quarantine model exists; full deterministic healing engine remains ahead.
Volume 7 | Anomaly Detection | PLANNED | App scaffold exists; feature implementation remains ahead.
Volume 8 | Forecasting | PLANNED | App scaffold exists; Prophet dependency is currently absent.
Volume 9 | CLV | PLANNED | App scaffold exists; XGBoost and btyd are currently absent.
Volume 10 | REST APIs | LOCALLY VERIFIED | Auth, /me/, and health behavior are tested; domain APIs are incomplete.
Volume 11 | Dashboard | PLANNED | App scaffold exists; full dashboard remains ahead.
Volume 12 | NLP Chatbot | PLANNED | App scaffold exists; full chatbot remains ahead.
Volume 13 | Testing Hardening | PLANNED | Later cross-project hardening remains.
Volume 14 | Deployment | PLANNED | Compose parses, but the complete stack was not shown running.
Volume 15 | Production Hardening | PLANNED | Not reached.
Volume 16 | Research Evaluation | PLANNED | Research/theory verification is separate from software tests.
Volume 17 | Documentation | REVIEW REQUIRED | Checkpoint and roadmap reconciled on 2026-10-11 to reflect committed 4.3.1; owner review remains pending. |  |  | Review the updated state, roadmap, and agent gate. | No
Volume 18 | Final Repository Review | PLANNED | Final audit remains ahead.